## Dashboard
Month-End Close Dashboard
Version: | v1.0
Last Updated: | 2026-02-01
Owner: | Armand Slabbert
RAG | Count | Critical Tasks | Count
Red | 5 | Critical Count | 14 Tasks
Amber | 6 | Red & Critical | 4 Tasks
Yellow | 1 | Amber & Critical | 5 Tasks
Green | 8
20
RAG Legend
Red = Not started / critical risk
Amber = Queries
Yellow = Work in progress / awaiting review
Green = Finalised

## Checklist
|  | Refer to tab Assumptions - EMPLOYEE | Refer to tab Assumptions - STATUS
Task Category | Task Description | Owner | Status | RAG | Critical Tasks | Due Date | Completed Date | Reviewed By | Notes
Pre-Close | Confirm month-end close timetable | Thabo Maseko | Not Started | Red | Yes | 2026-02-02 | 2026-02-28 | Thabo Maseko
Pre-Close | Ensure all source documents received | Annelie van Wyk | Pending Input | Amber | Yes | 2026-02-02 | 2026-02-28 | Annelie van Wyk
Cash & Banking | Perform bank reconciliations | Siphelele Dlamini | Finalised | Green | No | 2026-02-02 | 2026-02-28 | Siphelele Dlamini
Cash & Banking | Review outstanding reconciling items | Johan Botha | Not Started | Red | Yes | 2026-02-02 | 2026-02-28 | Johan Botha
Revenue | Verify revenue completeness and cut-off | Naledi Molefe | Pending Input | Amber | Yes | 2026-02-02 | 2026-02-28 | Naledi Molefe
Revenue | Reconcile revenue to sub-ledgers | Pieter du Plessis | Finalised | Green | Yes | 2026-02-02 | 2026-02-28 | Pieter du Plessis
Expenses | Capture all supplier invoices | Zandile Nkomo | Not Started | Red | Yes | 2026-02-02 | 2026-02-28 | Zandile Nkomo
Expenses | Review accruals and prepayments | Willem Pretorius | In Progress | Amber | No | 2026-02-02 | 2026-02-28 | Willem Pretorius
Payroll | Reconcile payroll to general ledger | Lerato Kgosi | Finalised | Green | Yes | 2026-02-02 | 2026-02-28 | Lerato Kgosi
Payroll | Review payroll accruals | Heinrich Müller | Not Started | Red | No | 2026-02-02 | 2026-02-28 | Heinrich Müller
Assets | Review fixed asset register | Busisiwe Zulu | Prepared | Yellow | Yes | 2026-02-02 | 2026-02-28 | Busisiwe Zulu
Assets | Post depreciation journals | Francois Joubert | Finalised | Green | Yes | 2026-02-02 | 2026-02-28 | Francois Joubert
Tax & VAT | Prepare VAT reconciliation | Kagiso Mokoena | In Progress | Amber | Yes | 2026-02-02 | 2026-02-28 | Kagiso Mokoena
Tax & VAT | Review VAT payable / receivable | Marlene Coetzee | Pending Input | Amber | Yes | 2026-02-02 | 2026-02-28 | Marlene Coetzee
Intercompany | Reconcile intercompany balances | Sibusiso Khumalo | Finalised | Green | No | 2026-02-02 | 2026-02-28 | Sibusiso Khumalo
Intercompany | Confirm intercompany agreements | Ruan de Villiers | Not Started | Red | Yes | 2026-02-02 | 2026-02-28 | Ruan de Villiers
Reporting | Prepare management accounts | Palesa Motsepe | Pending Input | Amber | Yes | 2026-02-02 | 2026-02-28 | Palesa Motsepe
Reporting | Perform variance analysis vs budget & prior month | Christo Nel | Finalised | Green | Yes | 2026-02-02 | 2026-02-28 | Christo Nel
Review | Finance Manager review & sign-off | Nomsa Madonsela | Finalised | Green | No | 2026-02-02 | 2026-02-28 | Nomsa Madonsela
Review | Final lock of accounting period | Arno Steyn | Finalised | Green | No | 2026-02-02 | 2026-02-28 | Arno Steyn
Note on D2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Refer to tab Assumptions - STATUS

## Assumptions - STATUS
Status | RAG | Column1 | Applies To | Key Assumptions | Control Requirement | Evidence Required
Not Started | Red | No | All close tasks | Period still open; no workpapers or journals created | No review or estimates permitted without approval | None
Pending Input | Amber | Yes | Tasks with external dependencies | Required information identified and outstanding | Follow-ups documented; estimates only if approved | Email trail / request log
In Progress | Amber | No | All operational close tasks | All source data received; work actively underway | Numbers provisional; not relied on for reporting | Draft schedules / reconciliations
Prepared | Yellow | No | All balance sheet reconciliations | Reconciliation balances to GL; no unexplained differences | Independent review required | Signed reconciliation + GL extract
Under Review | Yellow | Yes | All prepared close tasks | Reviewer actively assessing accuracy and completeness | No posting without reviewer approval | Review notes / checklist
Queries Raised | Yellow | Yes | Reviewed tasks with issues | Issues identified and communicated to preparer | All queries must be resolved before approval | Query log / email correspondence
Reworked / Updated | Yellow | Yes | Tasks returned after review | All review queries addressed; schedules updated | Must be re-reviewed before approval | Updated reconciliation + adjustment journals
Approved | Green | No | All close tasks | Reviewer satisfied; no unresolved differences | Numbers locked for reporting | Reviewer sign-off
Finalised | Green | No | Reporting and compliance outputs | Included in management pack; period locked | Changes require CFO approval | Management pack / submission confirmation

## Assumptions - EMPLOYEE
Owner & Reviewer | Job Title
Thabo Maseko | Chief Financial Officer
Annelie van Wyk | Finance Manager
Siphelele Dlamini | Senior Accountant
Johan Botha | Junior Accountant
Naledi Molefe | Bookkeeper
Pieter du Plessis | Creditors Clerk
Zandile Nkomo | Debtors Clerk
Willem Pretorius | Financial Controller
Lerato Kgosi | Management Accountant
Heinrich Müller | Group Reporting Accountant
Busisiwe Zulu | Payroll Administrator
Francois Joubert | Financial Analyst
Kagiso Mokoena | Assistant Accountant
Marlene Coetzee | Finance Administrator
Sibusiso Khumalo | Accounts Payable Supervisor
Ruan de Villiers | Treasury Analyst
Palesa Motsepe | Compliance & Reporting Officer
Christo Nel | Cost Accountant
Nomsa Madonsela | VAT & Tax Accountant
Arno Steyn | Internal Audit Officer
Lindiwe Mabaso | Finance Operations Coordinator
Jacques le Roux | Head of Finance Operations

## Useful tips
Accuracy & Risk Controls
Source System – trace every number back to origin
Amount / Exposure – supports value-based prioritisation
Material? (Yes/No) – enables risk-based review
Risk Rating (High/Medium/Low) – inherent risk vs execution status
Review & Audit Evidence
Reviewer Sign-off Date – proves independent review
Journal Ref / Batch ID – end-to-end traceability
Evidence Location – exact folder / link for audit speed
Exception & Change Management
Standard / Exception – explains deviations
Post-Close Adjustment? – protects you during audits
Depends On – removes premature reviews
Notes / Exception Log (already aligned with this structure)
Process Maturity Indicators
Recurring Task (Monthly / Quarterly / Annual / Ad-Hoc)
Automation Level (Manual / Semi-Automated / Automated)